## Slide 1: mSCOA ICF – 22 June 2015 Project Phase 4: Critical path leading to December 2015
Presented by National Treasury: Chief Directorate Local Government Budget Analysis: Carl Stroud |– 22 June 2015

## Slide 2: Critical deliverables (path) aligned to mSCOA Project Phase 4 work streams…next ten months!

## Slide 3
Oct to Dec 2015
(3 months)
July to Sep 2015
(3 months)
June 2015
May 2015
April 2015
March 2015
Work Stream 1: Technical
Finalise mSCOA Version 5.3 (all segments) – Lock down for piloting
Finalise selected position papers for adoption mSCOA Steer Com
Update SQL Version Manager
Develop draft BRF (MBRR), IYM and AFS templates including mapping of current IYM to mSCOA Version 5.3
Initial design framework for LG Database aligned to mSCOA
Continuous testing of LG Database mSCOA Version including SQL configuration and change management
Capacitation of NT Directorates – Two one day engagement including other stakeholders
NT consultation on refined reporting formats – BRF (MBRR, IYM and AFS)
Continuous development of position papers as project ramps up
Work Stream 2: Piloting
All work streams running concurrently!
Evaluation & assessment of pilots: System vendor and pilot municipality readiness (site visits)
Develop position paper on pilot assessment findings (possible TCF Paper)
Refine municipal risk register as a management tool
Engagements with pilot sites – Site visits to share findings and monitor pilot readiness
Issue formal communication on NT position as it relates to pilot readiness and risk
Piloting by selected municipalities
Finalise mSCOA Version 6 (all segments)
Update and release SQL Version Manager Version - 6
Lock down mSCOA Version 6
Compliance testing - Budgets, transacting and reporting
Site visits – Piloting munis
Formulation of NT position on piloting
mSCOA ICF
mSCOA ICF
mSCOA ICF

## Slide 4
Oct to Dec 2015
(3 months)
July to Sep 2015
(3 months)
June 2015
May 2015
April 2015
March 2015
Work Stream 3: Training
Finalise non-accredited training material (Pilots and vendors)
Work Stream 4: Transition
All work streams running concurrently!
Communications and change management strategy document – Develop and finalise
NT and mSCOA Project Team Training – 31 March
14 & 15 April
3 Sessions (KZN, Limpopo/Mpumulanga, Free State)
21 & 22 April
3 Sessions (Eastern Cape, Western Cape 1 & 2))
5 & 6 May
3 Sessions (Gauteng/North West, Metro 1 and 2)
1 day sesssions (Date TBA):
NT and other stakeholders
Development of Unit Standards
Registration of Unit Standards: LG SETA
Train the trainer?
Development of training material / text book
Certification of services providers (trainers)?
Develop training and information material for councilors including rollout strategy with SALGA
Site visits to all PT’s – Assessment of readiness in support of mSCOA
TCF Paper – Position of PT’s and action items going forward
Communication and change management as per strategy document including but not limited to:
Update FAQ SQL (Web based) and ensure maintenance
Circulars and general communication
Establish capacity gaps
Forums and support to PT’s

## Slide 5
Oct to Dec 2015
(3 months)
July to Sep 2015
(3 months)
June 2015
May 2015
April 2015
March 2015
Work Stream 5: LG Database
Mapping of current IYM to SCOA classification
All work streams running concurrently!
Defining data and report extraction formats
Development of parallel LG Database informed by data and report extraction formats
Testing of LG Database including among others:
Data and report extraction;
Reconciliation to current LG Database
Configuration and refinement
Engagement with Vendors and pilots
Testing of refined and amended reporting structures i.e. MBRR, IYM and AFS

## Slide 6: What does this mean for piloting, system vendors and non-piloting municipalities

## Slide 7
Jul
Work Stream 1: Piloting
Pilot sites: NT Testing
Pilot testing criteria to include:
Level of budget incorporation of all segments;
Third party system integration;
Transactional data across all segments;
Report extraction (statutory reports i.e. MBRR and IYM); and
Data extraction methodology.
The formulation of the migration strategy will include the following activities:
Engagements with each vendor in work shopping migration strategy (NT, PT’s and Vendor)
Finalisation of migration strategy
Scheduling user group sessions to workshop migration strategy
Migration strategy will include, among others:
  Roles, responsibilities, governance, timeframes, activities, cost implications,.
July 1, 2015
October 1, 2015
December 15, 2015
Aug
Oct
Sep
Dec
Nov
The following municipalities undertake piloting:
Senque;
Sol Plaatje
Elias Motsoaledi
Victor Khanye
Nkangala
Merafong;
Tlokwe;
Setsotho
uMgungundlovu
Richmon
uMhlatuze
Drakenstein
Overstrand
Bergrivier
Hessequa
Camedeboo
City of Cape Town;
Ekhurhuleni
Mangaung
Buffalo City
Greater Giyane
Pilot testing criteria
Formulation of migration strategy for non-piloting municipalities
NT to formulate and communicate final findings of assessment of system functionality in support of mSCOA classification framework – Close of the first quarter of the 2015/16 FY